## Overview
PROJECT NAME |  | MIETC | [5 empty] | Reported
PROJECT NUMBER |  | 610198-EPP-1-2019-1-ES-EPPKA2-CBHE-JP |  |  | Nº | Partner | Country | Staff Costs | S% | Travel Costs | S%2 | Costs of Stay | S%22 | Equipment | S%222 | Subcontrac. | S%2222 | Total
[5 empty] | P1 | USC | Spain | 24844 | 32.83% | 275 | 3.04% | 360 | 4.348% | 0 |  | 0 | 0% | 25479.4021
GRANT AWARDED |  |  | REPORTED | % REPORTED | P2 | Ayeconomics | Spain | 23010 | 44.74% | 0 | 0% | 0 | 0% | 0 |  | 0 |  | 23010.4474
1 | Staff Costs | 306847 | 112198 | 36.56% | P3 | UL | Slovenia | 5295 | 12.32% | 0 | 0% | 0 | 0% | 0 |  | 0 |  | 5295.1232
2 | Travel Costs | 198150 | 635 | 0.3205% | P4 | UNF | Italy | 33279 | 52.27% | 0 | 0% | 0 | 0% | 0 |  | 0 |  | 33279.5227
3 | Costs of Stay | 239280 | 840 | 0.3511% | P5 | EKTU | Kazakhstan | 6416 | 39.41% | 0 | 0% | 0 | 0% | 3766.2406 | 25.49% | 0 | 0% | 10182.8896
4 | Equipement Costs | 39777 | 19112.6912 | 48.05% | P6 | AST | Turkmenistan | 5556 | 38.07% | 0 | 0% | 0 | 0% | 0 |  | 785.6696 | 14.39% | 6342.0502
5 | Subcontracting costs | 22960 | 785.6696 | 3.422% | P7 | TSIEM | Turkmenistan | 1128 | 20.25% | 0 | 0% | 0 | 0% | 4894.5 | 97.89% | 0 | 0% | 6023.6814
A | Grant for project activities | 807014 | 133571.3608 | 16.55% | P8 | TSIF | Turkmenistan | 1720 | 30.88% | 0 | 0% | 0 | 0% | 4894.5 | 97.89% | 0 | 0% | 6615.7877
B | Additional Grant for Special Mobility Strand |  |  |  | P9 | KUK | Kazakhstan | 4705 | 33.23% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 4705.3323
| Total Grant requested from the European Union (A+B) | 807014 |  |  | P10 | TUT | Tajikistan | 2442 | 37.4% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 2442.374
[5 empty] | P11 | TSUC | Tajikistan | 3521 | 41.67% | 360 | 1.491% | 480 | 1.487% | 5557.4506 | 111.1% | 0 | 0% | 9920.0086
[5 empty] | P12 | CTAST | Turkmenistan | 282 | 40% | 0 | 0% | 0 | 0% | 0 |  | 0 |  | 282.4
[5 empty] | P13 | FANOVAR | Tajikistan | 0 | 0% | 0 | 0% | 0 | 0% | 0 |  | 0 |  | 0
[5 empty] | P14 | ECBP | Kazakhstan | 0 | 0% | 0 | 0% | 0 | 0% | 0 |  | 0 |  | 0
[8 empty] | 112198 | 36.56% | 635 | 0.3205% | 840 | 0.3511% | 19112.6912 | 48.05% | 785.6696 | 3.422% | 133579.0192
GRANT AWARDED
[5 empty] | Nº | Partner | Country | Staff Costs | Travel Costs | Costs of Stay | Equipment | Subcontrac. | Total
[5 empty] | P1 | University of Santiago de Compostela (USC) | Spain | 75685 | 9045 | 8280 | - | 12500 | 105510
[5 empty] | P2 | Ayeconomics Research Centre S.L. | Spain | 51435 | 8770 | 7920 | - | - | 68125
[5 empty] | P3 | University of Ljubljana (UL) | Slovenia | 42962 | 8495 | 7800 | - | - | 59257
[5 empty] | P4 | University of Naples Federico II (UNF) | Italy | 63665 | 8770 | 8160 | - | - | 80595
[5 empty] | P5 | East-Kazakhstan State Technical University (EKTSU) | Kazakhstan | 16280 | 24340 | 32520 | 14777 | 1000 | 88917
[5 empty] | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | 14595 | 6570 | 5040 | - | 5460 | 31665
[5 empty] | P7 | Turkmen State Institute of Economics and Management (TSIEM) | Turkmenistan | 5570 | 23790 | 31800 | 5000 | 500 | 66660
[5 empty] | P8 | Turkmen State Institute of Finance (TSIF) | Turkmenistan | 5570 | 23790 | 31800 | 5000 | 500 | 66660
[5 empty] | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | 14160 | 24340 | 32520 | 5000 | 1000 | 77020
[5 empty] | P10 | Technological University of Tajikistan (TUT) | Tajikistan | 6530 | 23790 | 31800 | 5000 | 1000 | 68120
[5 empty] | P11 | Tajik State University of Tajikistan (TSUC) | Tajikistan | 8450 | 24150 | 32280 | 5000 | 1000 | 70880
[5 empty] | P12 | CTAST | Turkmenistan | 705 | 4100 | 3120 | - | - | 7925
[5 empty] | P13 | FANOVAR | Tajikistan | 470 | 4100 | 3120 | - | - | 7690
[5 empty] | P14 | ECBP | Kazakhstan | 770 | 4100 | 3120 | - | - | 7990
[8 empty] | 306.847,00 € | 198.150,00 € | 239.280,00 € | 39.777,00 € | 22.960,00 € | 807.014,00 €

## Staff Costs
WORK PACKAGE | PARTNER NUMBER | NAME OF PARTNER | COUNTRY | SUPPORTING DOCUMENT | NAME OF STAFF MEMBER | STAFF CATEGORY | WP/Task | SHORT DESCRIPTION OF TASKS | FROM | TO | NUMBER OF DAYS | MAX. UNIT COST PER DAY | TOTAL CALCULATED
Management | P1 | University of Santiago de Compostela (USC) | Spain | 1.1 | Sonia Cordido Méndez | Administrative staff | WP1 | Kick-off meeting organization and planning: logistical aspects, preparation of the agenda, coordination of presentations and participants. Compilation of working teams list and contact lists. Internal financial managemnt of the grant and budget allocation. Kick-off meeting organization and planning. | 2020-01-15 | 2020-07-14 | 7 | 78 | 546
Preparation | P1 | University of Santiago de Compostela (USC) | Spain | 1.2 | Sonia Cordido Méndez | Manager | WP2 | Development of the Work Plan of the project. | 2020-01-15 | 2020-07-14 | 6 | 164 | 984
Management | P1 | University of Santiago de Compostela (USC) | Spain | 1.3 | Ángel Duarte Campos | Administrative staff | WP1 | Preparation and participation in the KoM. Presentation of technical, financial and administrative management and of the QAS. Preparation of detailed KoM minutes and follow-up actions. Drafting PAs and discussion with Partners. Setting up internal communication channels (Slack, email lists, online repository). Preparing budget amendment request. Transfers to partners. | 2020-01-15 | 2020-07-14 | 10 | 78 | 780
Quality Plan | P1 | University of Santiago de Compostela (USC) | Spain | 1.3 | Ángel Duarte Campos | Administrative staff | WP4 | Quality Control and monitoring of the project's implementation and outputs. Preparing document templates to ensure format consistency (deliverables, agenda, presentations, etc.). Quality Control and monitoring of the project's implementation and outputs. | 2020-01-15 | 2020-07-14 | 5 | 78 | 390
Dissemination & Exploitation | P1 | University of Santiago de Compostela (USC) | Spain | 1.3 | Ángel Duarte Campos | Administrative staff | WP5 | Publication about the KoM on USC's website and social media. Revision of the Dissemination Strategy and feedback. Publication of news item about the online workshops with stakeholders in TKM and KZ. Reviewing and providing content for the project website. | 2020-01-15 | 2020-07-14 | 3 | 78 | 234
Management | P1 | University of Santiago de Compostela (USC) | Spain | 1.4 | Ángel Duarte Campos | Manager | WP1 | Day-to-day internal communication with Partners and project management. Elaboration of the internal communication and coordination plan (regulatory framework, distributed management, meetings and operation, internal communication channels, conflict resolution mechanisms). Elaboration of the Financianl and administrative management guide (transfer and reimbursement procedures, financial management of the Grant, reporting obligations, good practices). Participation in online meeting of the Dissemination Board (website and visual identity). | 2020-01-15 | 2020-07-14 | 21 | 164 | 3444
Preparation | P1 | University of Santiago de Compostela (USC) | Spain | 1.4 | Ángel Duarte Campos | Manager | WP2 | Development of the Work Plan of the project. Nominations for the distributed management bodies and compilation of member lists (MB, AC, DB, ECM). Presentation about WP2 on the kick-off meeting (implementation plan, accounting and monitoring mechanisms). Development of the Implementation Plan (detailed task distribution, task description, calendarization). Updating and monitoring the development of the Work Plan. Participation in online workshops with KZ and TKM stakeholders. | 2020-01-15 | 2020-07-14 | 24 | 164 | 3936
Development | P1 | University of Santiago de Compostela (USC) | Spain | 1.4 | Ángel Duarte Campos | Manager | WP3 | Compiling information about the accreditation process in KZ, TJ and TKM. | 2020-01-15 | 2020-07-14 | 1 | 164 | 164
Quality Plan | P1 | University of Santiago de Compostela (USC) | Spain | 1.4 | Ángel Duarte Campos | Manager | WP4 | Preparing Quality Assurance Plan. Defining Quality Assurance Framework for each task. | 2020-01-15 | 2020-07-14 | 3 | 164 | 492
Preparation | P1 | University of Santiago de Compostela (USC) | Spain | 1.5 | Manuel Fernández Grela | Researcher/Teacher/Trainer | WP2 | Analysis of International Master Programmes | 2020-01-15 | 2020-07-14 | 4 | 137 | 548
Development | P1 | University of Santiago de Compostela (USC) | Spain | 1.5 | Manuel Fernández Grela | Researcher/Teacher/Trainer | WP3 | Preparation of Content Development Strategy for Kick-Off Meeting | 2020-01-15 | 2020-07-14 | 2 | 137 | 274
Preparation | P1 | University of Santiago de Compostela (USC) | Spain | 1.6 | Ángel Duarte Campos | Technical Staff | WP2 | Setting up accounting and monitoring mechanisms (interactive spreadsheets). | 2020-01-15 | 2020-07-14 | 10 | 102 | 1020
Management | P1 | University of Santiago de Compostela (USC) | Spain | 1.7 | Ángel Duarte Campos | Administrative staff | WP1 | Revision, compilation and consolidation of budget expenditure reports. Drafting Partnership Agreement Amendments. Drafting tripartite contract for the purchase of TKM HEIs Equipment and discussion with Partners. Transfers to partners. Internal meetings with USC Financial & Hiring Department. Execution of the tripartite contract for the purchase of TKM HEIs Equipment. | 2020-07-15 | 2021-01-14 | 12 | 78 | 936
Quality Plan | P1 | University of Santiago de Compostela (USC) | Spain | 1.7 | Ángel Duarte Campos | Administrative staff | WP4 | Quality Control and monitoring of the project's implementation and outputs. | 2020-07-15 | 2021-01-14 | 14 | 78 | 1092
Dissemination & Exploitation | P1 | University of Santiago de Compostela (USC) | Spain | 1.7 | Ángel Duarte Campos | Administrative staff | WP5 | Preparing dissemination report for the 1st period (specific dissemination actions). Reviewing the 1st project newsletter and providing feedback. Publication of news item in reference to the participation in Cluster Meeting. | 2020-07-15 | 2021-01-14 | 2 | 78 | 156
Preparation | P1 | University of Santiago de Compostela (USC) | Spain | 1.8 | Manuel Fernández Grela | Researcher/Teacher/Trainer | WP2 | Analysis of International Master Programmes | 2020-07-15 | 2021-01-14 | 11 | 137 | 1507
Development | P1 | University of Santiago de Compostela (USC) | Spain | 1.8 | Manuel Fernández Grela | Researcher/Teacher/Trainer | WP3 | Participation in online meeting to discuss development of WP3. Revision of Sustainability Strategy. Development of the Curriculum. | 2020-07-15 | 2021-01-14 | 13 | 137 | 1781
Management | P1 | University of Santiago de Compostela (USC) | Spain | 1.9 | Ángel Duarte Campos | Manager | WP1 | Elaboration of the Financianl and administrative management guide. Day-to-day internal communication with Partners and project management. Preparation, organization and participation on online project meeting. | 2020-07-15 | 2021-01-14 | 15 | 164 | 2460
Preparation | P1 | University of Santiago de Compostela (USC) | Spain | 1.9 | Ángel Duarte Campos | Manager | WP2 | Updating and monitoring the development of the Work Plan. | 2020-07-15 | 2021-01-14 | 5 | 164 | 820
Development | P1 | University of Santiago de Compostela (USC) | Spain | 1.9 | Ángel Duarte Campos | Manager | WP3 | Compiling information about the accreditation process in KZ, TJ and TKM. | 2020-07-15 | 2021-01-14 | 2 | 164 | 328
Quality Plan | P1 | University of Santiago de Compostela (USC) | Spain | 1.9 | Ángel Duarte Campos | Manager | WP4 | Preparing Quality Assurance Plan. Defining Quality Assurance Framework for each task. Completing EACEA's survey on implementation status. | 2020-07-15 | 2021-01-14 | 18 | 164 | 2952
0
Management | P2 | Ayeconomics Research Centre S.L. | Spain | P2.1 | Aizhan Samambayeva | Manager | WP1 | Kick-off meeting preparation, management of partners to provide data, preparing and presenting results of Market need analysis (online info day) | 2020-01-15 | 2020-07-14 | 5 | 164 | 820
Quality Plan | P2 | Ayeconomics Research Centre S.L. | Spain | P2.1 | Aizhan Samambayeva | Manager | WP4 | Revising, commenting and editing strategy | 2020-01-15 | 2020-07-14 | 5 | 164 | 820
Preparation | P2 | Ayeconomics Research Centre S.L. | Spain | P2.2 | Aizhan Samambayeva | Researcher/Teacher/Trainer | WP2 | Developing Market needs strategy, data gathering of labour market indicators Tajikistan, Kazakhstan, Turkmenistan. Harmonisation of data, Providing descriptive statistics, Providing conclusions | 2020-01-15 | 2020-07-14 | 40 | 137 | 5480
Preparation | P2 | Ayeconomics Research Centre S.L. | Spain | P2.3 | Iria Dios Murcia | Researcher/Teacher/Trainer | WP2 | List of indicators per country, info day and preliminary results presentation for Turkmenistan and Kazakhstan | 2020-01-15 | 2020-07-14 | 12 | 137 | 1644
Preparation | P2 | Ayeconomics Research Centre S.L. | Spain | P2.4 | Yolanda Pena-Boquete | Researcher/Teacher/Trainer | WP2 | Market needs strategy, list of indicators per country, presentation of market needs strategy, info day and preliminary results presentation for Turkmenistan and Kazakhstan | 2020-01-15 | 2020-07-14 | 41 | 137 | 5617
Quality Plan | P2 | Ayeconomics Research Centre S.L. | Spain | P2.5 | Aizhan Samambayeva | Manager | WP4 | Preparing Draft: Describing challenges and the strategies implemented to overcome challenges. Conducting qualitative and quantitative indicators for tasks 2.1. 2.2. 2.3. Sending to parterns for feedback and draft improvent. Providing conclusion and proposal for furhter improvement. Formattinag and publishing reports. | 2020-07-15 | 2021-01-14 | 5 | 164 | 820
Development | P2 | Ayeconomics Research Centre S.L. | Spain | P2.6 | Aizhan Samambayeva | Researcher/Teacher/Trainer | WP3 | Providing feedback to Market needs analysis. Developing curriculum for Master Program. Formulatig main concept and needs of the market in Innovation Management. Define aim and objectives, description of the subject. | 2020-07-15 | 2021-01-14 | 20 | 137 | 2740
Preparation | P2 | Ayeconomics Research Centre S.L. | Spain | P2.7 | Iria Dios Murcia | Researcher/Teacher/Trainer | WP2 | Design of survey for Delphi analysis (first round), validation with the partners and incorporation of the suggestions. ImplementaKon of 1st round of Delphi analysis using QuestionPro platform, which allows anonymize the responses and logic in the questions. Design of infographics to increase the dissemination of the main results. Preparation of the competence analysis document and validation with the partner. Analysis of the results of the first round and incorporation of the results to updating survey for designing 2nd round of the survey. Analysis of the second round results and incorporation to the market need full-document. | 2020-07-15 | 2021-01-14 | 16 | 137 | 2192
Preparation | P2 | Ayeconomics Research Centre S.L. | Spain | P2.8 | Yolanda Pena-Boquete | Researcher/Teacher/Trainer | WP2 | Updating of the DELPHI analysis time line. Meeting to be coordinated with local partners and be more efficient applying the survey taking into account COVID-19 limitations. | 2020-07-15 | 2021-01-14 | 1 | 137 | 137
Development | P2 | Ayeconomics Research Centre S.L. | Spain | P2.8 | Yolanda Pena-Boquete | Researcher/Teacher/Trainer | WP3 | Analysis of the preliminary results of market needs for targeJng the subjects that should be in the master curriculum. StarJng the development of the curriculum. Development of the curriculum. | 2020-07-15 | 2021-01-14 | 20 | 137 | 2740
0
Management | P3 | University of Ljubljana (UL) | Slovenia | P3.1 | Tomaž Čater | Manager | WP1 | Attending Kick-off meeting. Internal communication and coordination of the project with SEB LU adminstration. | 2020-03-01 | 2020-03-31 | 3 | 164 | 492
Preparation | P3 | University of Ljubljana (UL) | Slovenia | P3.2 | Tomaž Čater | Researcher/Teacher/Trainer | WP2 | Analysis of needs and competences for international Master program | 2020-02-03 | 2020-04-30 | 9 | 137 | 1233
Development | P3 | University of Ljubljana (UL) | Slovenia | P3.2 | Tomaž Čater | Researcher/Teacher/Trainer | WP3 | Development of the curriculum frame for international Master program | 2020-02-03 | 2020-04-30 | 6 | 137 | 822
Management | P3 | University of Ljubljana (UL) | Slovenia | P3.3 | Klavdija Besednjak | Administrative staff | WP1 | Administrative tasks of the project, colletion of information, monitoring and reviewing of project documentation. | 2020-07-15 | 2021-01-14 | 10 | 78 | 780
Management | P3 | University of Ljubljana (UL) | Slovenia | P3.4 | Mojca Maher Pirc | Manager | WP1 | Financial management of project activities and administration, communication activites related to project management. Participation in project meetings. | 2020-07-15 | 2021-01-14 | 8 | 164 | 1312
Management | P3 | University of Ljubljana (UL) | Slovenia | P3.5 | Tomaž Čater | Manager | WP1 | Analysis and commenting on Dissemination strategy. Internal communication and coordination of MIETC project with SEB LU administration. | 2020-07-15 | 2021-01-14 | 4 | 164 | 656
0
Management | P4 | University of Naples Federico II (UNF) | Italy | P4.1 | Carmela Gargiulo | Manager | WP1 | Project Internal communication and coordination - sharing information with other partner. Kick off Meeting. Partecipation to market analysis presentation AYE. Website presentation with partner. Defining Members for each management board. Quality plan- defining procedur and layout. | 2020-01-15 | 2020-07-14 | 9 | 280 | 2520
Preparation | P4 | University of Naples Federico II (UNF) | Italy | P4.1 | Carmela Gargiulo | Manager | WP2 | Project Internal communication and coordination - sharing information with other partner. Kick off Meeting. Partecipation to market analysis presentation AYE. Website presentation with partner. Defining Members for each management board. Quality plan- defining procedur and layout. | 2020-01-15 | 2020-07-14 | 5 | 280 | 1400
Quality Plan | P4 | University of Naples Federico II (UNF) | Italy | P4.1 | Carmela Gargiulo | Manager | WP4 | Project Internal communication and coordination - sharing information with other partner. Kick off Meeting. Partecipation to market analysis presentation AYE. Website presentation with partner. Defining Members for each management board. Quality plan- defining procedur and layout. | 2020-01-15 | 2020-07-14 | 4 | 280 | 1120
Preparation | P4 | University of Naples Federico II (UNF) | Italy | P4.2 | Gerardo Carpentieri | Researcher/Teacher/Trainer | WP2 | Analysis of international Mater porgrams - Selection of Master programs in Industrial Enterpreneurship sector | 2020-01-15 | 2020-07-14 | 5 | 214 | 1070
Dissemination & Exploitation | P4 | University of Naples Federico II (UNF) | Italy | P4.3 | Gerardo Carpentieri | Technical Staff | WP5 | Web site and visual identity - defining of layout and main section of Mietc Web | 2020-01-15 | 2020-07-14 | 3 | 162 | 486
Preparation | P4 | University of Naples Federico II (UNF) | Italy | P4.4 | Carmen Guida | Researcher/Teacher/Trainer | WP2 | Analysis of international Mater programs report about offers and suggestions for developing MIETC master program | 2020-01-15 | 2020-07-14 | 5 | 214 | 1070
Dissemination & Exploitation | P4 | University of Naples Federico II (UNF) | Italy | P4.5 | Federica Gaglione | Technical Staff | WP5 | Social Media and communication - Opening the social maedia account (instagram, twitter, Facebook and youtube) | 2020-01-15 | 2020-07-14 | 2 | 162 | 324
Preparation | P4 | University of Naples Federico II (UNF) | Italy | P4.6 | Federica Gaglione | Researcher/Teacher/Trainer | WP2 | Analysis of international Master programs Organization of selected master programs | 2020-01-15 | 2020-07-14 | 5 | 214 | 1070
Management | P4 | University of Naples Federico II (UNF) | Italy | P4.7 | Stefania Volpe | Administrative staff | WP1 | Kick off Meeting. Financial management and administration - suporting project oordination and management action. Web site and visual identity. Finalizing hosting web site procedure | 2020-01-15 | 2020-07-14 | 9 | 131 | 1179
Dissemination & Exploitation | P4 | University of Naples Federico II (UNF) | Italy | P4.7 | Stefania Volpe | Administrative staff | WP5 | Kick off Meeting. Financial management and administration - suporting project oordination and management action. Web site and visual identity. Finalizing hosting web site procedure | 2020-01-15 | 2020-07-14 | 12 | 131 | 1572
Dissemination & Exploitation | P4 | University of Naples Federico II (UNF) | Italy | P4.8 | Gerardo Carpentieri | Technical Staff | WP5 | Web site and visual identity - Defining of layout and main sections of MIETC web site. WP 5.5 Social media and communication. | 2020-07-15 | 2021-01-14 | 3 | 162 | 486
Development | P4 | University of Naples Federico II (UNF) | Italy | P4.9 | Federica Gaglione | Researcher/Teacher/Trainer | WP3 | Development of the curriculum for the Master Program. Content development. Content development. | 2020-07-15 | 2021-01-14 | 25 | 214 | 5350
Management | P4 | University of Naples Federico II (UNF) | Italy | P4.10 | Carmela Gargiulo | Manager | WP1 | Project internal communication and coordination - sharing information with other partners. | 2020-07-15 | 2021-01-14 | 6 | 280 | 1680
Quality Plan | P4 | University of Naples Federico II (UNF) | Italy | P4.10 | Carmela Gargiulo | Manager | WP4 | Quality Plan - defining procedura and layout. Periodical reports. | 2020-07-15 | 2021-01-14 | 6 | 280 | 1680
Development | P4 | University of Naples Federico II (UNF) | Italy | P4.11 | Carmen Guida | Researcher/Teacher/Trainer | WP3 | Development of the curriculum of the Master Program. Content development. | 2020-07-15 | 2021-01-14 | 23 | 214 | 4922
Management | P4 | University of Naples Federico II (UNF) | Italy | P4.12 | Stefania Volpe | Administrative staff | WP1 | Financial management and administration - supporting project coordination and management actions | 2020-07-15 | 2021-01-14 | 7 | 131 | 917
Quality Plan | P4 | University of Naples Federico II (UNF) | Italy | P4.12 | Stefania Volpe | Administrative staff | WP4 | Periodical reports | 2020-07-15 | 2021-01-14 | 5 | 131 | 655
Development | P4 | University of Naples Federico II (UNF) | Italy | P4.13 | Gerardo Carpentieri | Researcher/Teacher/Trainer | WP3 | Development of the curriculum of the Master Program. Content development. | 2020-07-15 | 2021-01-14 | 27 | 214 | 5778
[12 empty] | 0 | 0
Preparation | P5 | East-Kazakhstan State Technical University (EKTSU) | Kazakhstan | P5.1 | Zhadyra Konurbayeva | Manager | WP2 | Analysis of needs of the project, Analysis of competences on the regional labor market. | 2020-01-15 | 2020-07-14 | 5 | 77 | 385
Management | P5 | East-Kazakhstan State Technical University (EKTSU) | Kazakhstan | P5.1 | Zhadyra Konurbayeva | Manager | WP1 | Kick-off meeting - online organization, Project internal communication and coordination, Financial management and administration . | 2020-01-15 | 2020-07-14 | 5 | 77 | 385
Management | P5 | East-Kazakhstan State Technical University (EKTSU) | Kazakhstan | P5.2 | Zhassulan Shaimardanov | Manager | WP1 | Analysis of needs of the project, Project internal communication and coordination, Kick-off meeting - online organization, Preparation progress reports, Financial management and administration | 2020-01-15 | 2020-07-14 | 10 | 77 | 770
Management | P5 | East-Kazakhstan State Technical University (EKTSU) | Kazakhstan | P5.3 | Saule Rakhmetullina | Administrative staff | WP1 | Analysis of needs of the project, Participate in the needs and competences analysis surveys, Kick-off meeting - online organization, Implement Workshops/Survey with stakeholders, Preparation progress reports | 2020-01-15 | 2020-07-14 | 10 | 32 | 320
Development | P5 | East-Kazakhstan State Technical University (EKTSU) | Kazakhstan | P5.4 | Madina Yussubaliyeva | Researcher/Teacher/Trainer | WP2 | Needs analysis, Kick-off meeting - online organization, Strategy of English language training. List of participants. Participation in kick off meeting, Collection of information, monitoring of project documentation, Implement a course on Coursera for EKSTU"Improve your communication skills" to improve English of teachers for Central Asia academic partners. Application process for Coursera course in the frame of program, Design ESP course to improve English of teachers for Central Asia academic partners. Half year report. Reports. Launching agreement process for perchasing English Discoveries. | 2020-01-15 | 2020-07-14 | 7 | 57 | 399
Management | P5 | East-Kazakhstan State Technical University (EKTSU) | Kazakhstan | P5.4 | Madina Yussubaliyeva | Researcher/Teacher/Trainer | WP1 | Needs analysis, Kick-off meeting - online organization, Strategy of English language training. List of participants. Participation in kick off meeting, Collection of information, monitoring of project documentation, Implement a course on Coursera for EKSTU"Improve your communication skills" to improve English of teachers for Central Asia academic partners. Application process for Coursera course in the frame of program, Design ESP course to improve English of teachers for Central Asia academic partners. Half year report. Reports. Launching agreement process for perchasing English Discoveries. | 2020-01-15 | 2020-07-14 | 5 | 57 | 285
Management | P5 | East-Kazakhstan State Technical University (EKTSU) | Kazakhstan | P5.5 | Elvira Madiyarova | Researcher/Teacher/Trainer | WP1 | Selection of educational literature for the preparation of the program of English language courses, selection of statistical data for marketing analysis, maintaining project documentation, participation in the preparation and conduct of various project activities | 2020-01-15 | 2020-07-14 | 8 | 57 | 456
Management | P5 | East-Kazakhstan State Technical University (EKTSU) | Kazakhstan | P5.6 | Marina Kozlova | Administrative staff | WP1 | Selection of educational literature for the preparation of the program of English language courses, selection of statistical data for marketing analysis, work on the content and content of the University website that informs about the project | 2020-01-15 | 2020-07-14 | 8 | 32 | 256
Development | P5 | East-Kazakhstan State Technical University (EKTSU) | Kazakhstan | P5.7 | Elvira Madiyarova | Researcher/Teacher/Trainer | WP3 | Oranize events/seminars/surveys among stakeholders. Statistics for market need analysis. Primary design of the Master degree program curriculum. Process of certification and accreditation. | 2020-07-15 | 2021-01-14 | 10 | 57 | 570
Management | P5 | East-Kazakhstan State Technical University (EKTSU) | Kazakhstan | P5.8 | Madina Rakhimberdinova | Administrative staff | WP1 | Work on the dissemination of information about the events and placement of social media accounts. Creating and updating informationon on website of the project and the university. Preparation of content material for public placement. | 2020-07-15 | 2021-01-14 | 5 | 32 | 160
Development | P5 | East-Kazakhstan State Technical University (EKTSU) | Kazakhstan | P5.9 | Madina Yussubaliyeva | Researcher/Teacher/Trainer | WP3 | Administrating and resiving English Language training Strategy. Lauching LMS OLS for the EL course by redesigning programs for trainees with beginner, elementary, intermediate and advanced level of English language. Organizing OLS orientation meetings for CA partners. Preparing reports fro addresing and resolving existing problems of EL training. Designed online course on Academic listening and speaking for CA partners. Enrolment of participants. | 2020-07-15 | 2021-01-14 | 10 | 57 | 570
Management | P5 | East-Kazakhstan State Technical University (EKTSU) | Kazakhstan | P5.10 | Saule Rakhmetullina | Administrative staff | WP1 | Communication with stakeholders of the project. Conducting analytical studies on the needs of the project's target audience.Organizing meetings with representatives of the enterprise and business to particpate in the study of market needs. Writing recommendations on the content of the education program. | 2020-07-15 | 2021-01-14 | 10 | 32 | 320
Management | P5 | East-Kazakhstan State Technical University (EKTSU) | Kazakhstan | P5.11 | Zhassulan Shaimardanov | Manager | WP1 | Coordination of team activities in achieving the main objectives of the project. Online meeting preparation. Financial and admi nistrative issues. Reporting. | 2020-07-15 | 2021-01-14 | 10 | 77 | 770
Management | P5 | East-Kazakhstan State Technical University (EKTSU) | Kazakhstan | P5.12 | Zhadyra Konurbayeva | Manager | WP1 | Organization of the process of teaching English to EKTU teachers. Assistance in making up their training schedule. Monitoring attendance. Organizing meeting with stakeholders to participate in the Survey. Conducting presonal interviews with representatives of industrial enterprises and government agencies. Equipment purchase and state procurement procedure. Report on accreditation procedure. | 2020-07-15 | 2021-01-14 | 10 | 77 | 770
[12 empty] | 0 | 0
Development | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.1 | Charyyar Amansahedov | Administrative staff | WP3 | Project internal communication with inner and interregional partners, Participation to the online Kick Off meeting Dissemination strategy circulation, feedback from Partners, inner meeting, Project coordination and management action support, TKM side Project coordination and management action support, Quality Plan following and implementation Analysis of needs and competences actions support, English language training program participation, Preparedness to MIETC the articles and publications, Project internal communication and coordination in connection with June 12-th international conference, Inner discussion on TKM partners needs and competences, English language improving proficiency Preparation for development of the curriculum for the Master Program, Review of the Project professional network | 2020-01-15 | 2020-07-14 | 6 | 17 | 102
Dissemination & Exploitation | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.1 | Charyyar Amansahedov | Administrative staff | WP5 | Project internal communication with inner and interregional partners, Participation to the online Kick Off meeting Dissemination strategy circulation, feedback from Partners, inner meeting, Project coordination and management action support, TKM side Project coordination and management action support, Quality Plan following and implementation Analysis of needs and competences actions support, English language training program participation, Preparedness to MIETC the articles and publications, Project internal communication and coordination in connection with June 12-th international conference, Inner discussion on TKM partners needs and competences, English language improving proficiency Preparation for development of the curriculum for the Master Program, Review of the Project professional network | 2020-01-15 | 2020-07-14 | 8 | 17 | 136
Management | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.1 | Charyyar Amansahedov | Administrative staff | WP1 | Project internal communication with inner and interregional partners, Participation to the online Kick Off meeting Dissemination strategy circulation, feedback from Partners, inner meeting, Project coordination and management action support, TKM side Project coordination and management action support, Quality Plan following and implementation Analysis of needs and competences actions support, English language training program participation, Preparedness to MIETC the articles and publications, Project internal communication and coordination in connection with June 12-th international conference, Inner discussion on TKM partners needs and competences, English language improving proficiency Preparation for development of the curriculum for the Master Program, Review of the Project professional network | 2020-01-15 | 2020-07-14 | 3 | 17 | 51
Preparation | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.1 | Charyyar Amansahedov | Administrative staff | WP2 | Project internal communication with inner and interregional partners, Participation to the online Kick Off meeting Dissemination strategy circulation, feedback from Partners, inner meeting, Project coordination and management action support, TKM side Project coordination and management action support, Quality Plan following and implementation Analysis of needs and competences actions support, English language training program participation, Preparedness to MIETC the articles and publications, Project internal communication and coordination in connection with June 12-th international conference, Inner discussion on TKM partners needs and competences, English language improving proficiency Preparation for development of the curriculum for the Master Program, Review of the Project professional network | 2020-01-15 | 2020-07-14 | 9 | 17 | 153
Quality Plan | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.1 | Charyyar Amansahedov | Administrative staff | WP4 | Project internal communication with inner and interregional partners, Participation to the online Kick Off meeting Dissemination strategy circulation, feedback from Partners, inner meeting, Project coordination and management action support, TKM side Project coordination and management action support, Quality Plan following and implementation Analysis of needs and competences actions support, English language training program participation, Preparedness to MIETC the articles and publications, Project internal communication and coordination in connection with June 12-th international conference, Inner discussion on TKM partners needs and competences, English language improving proficiency Preparation for development of the curriculum for the Master Program, Review of the Project professional network | 2020-01-15 | 2020-07-14 | 2 | 17 | 34
Development | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.2 | Rustam Gadzhiyev | Manager | WP3 | Inner TKMs Project’s implementation plan, overall preparation to the project implementation, Developing dissemination strategy (drat document), Inner TKM project team meeting, Developing dissemination strategy (permanent communication to all project partners), Support dor Defining Management Board, Dissemination board (DB), Academic Board (AB), Entrepreneurship Centre Manager (ECM), Task Core Groups (TCGs), Dissemination Strategy correspondence, discussion and elaboration, Support for preparation of English language training program and Improving English proficiency of academic staff, Project internal communication with inner and interregional partners, English language training program and Improving English proficiency of academic staff, Participation in the Kick Off Meeting (online, via Zoom), Dissemination strategy circulation, feedback from Partners, Project coordination and management action support, Support for the Project coordination and management, Support for Development of guidelines for target group survey, information delivering to Ayeconomics, Periodical reports implementation, Analysis of needs and competences actions support, English language training program participation, Action dissemination at the international online conference, Support for inner financial management and administration, Inner discussion on TKM partners needs and competences, International Conference participation and project action dissemination (Ashgabat June 12-13, 2020), English language proficiency improving, Periodical reports implementation, Social media and communication review and actions support. | 2020-01-15 | 2020-07-14 | 7 | 47 | 329
Dissemination & Exploitation | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.2 | Rustam Gadzhiyev | Manager | WP5 | Inner TKMs Project’s implementation plan, overall preparation to the project implementation, Developing dissemination strategy (drat document), Inner TKM project team meeting, Developing dissemination strategy (permanent communication to all project partners), Support dor Defining Management Board, Dissemination board (DB), Academic Board (AB), Entrepreneurship Centre Manager (ECM), Task Core Groups (TCGs), Dissemination Strategy correspondence, discussion and elaboration, Support for preparation of English language training program and Improving English proficiency of academic staff, Project internal communication with inner and interregional partners, English language training program and Improving English proficiency of academic staff, Participation in the Kick Off Meeting (online, via Zoom), Dissemination strategy circulation, feedback from Partners, Project coordination and management action support, Support for the Project coordination and management, Support for Development of guidelines for target group survey, information delivering to Ayeconomics, Periodical reports implementation, Analysis of needs and competences actions support, English language training program participation, Action dissemination at the international online conference, Support for inner financial management and administration, Inner discussion on TKM partners needs and competences, International Conference participation and project action dissemination (Ashgabat June 12-13, 2020), English language proficiency improving, Periodical reports implementation, Social media and communication review and actions support. | 2020-01-15 | 2020-07-14 | 11 | 47 | 517
Management | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.2 | Rustam Gadzhiyev | Manager | Wp1 | Inner TKMs Project’s implementation plan, overall preparation to the project implementation, Developing dissemination strategy (drat document), Inner TKM project team meeting, Developing dissemination strategy (permanent communication to all project partners), Support dor Defining Management Board, Dissemination board (DB), Academic Board (AB), Entrepreneurship Centre Manager (ECM), Task Core Groups (TCGs), Dissemination Strategy correspondence, discussion and elaboration, Support for preparation of English language training program and Improving English proficiency of academic staff, Project internal communication with inner and interregional partners, English language training program and Improving English proficiency of academic staff, Participation in the Kick Off Meeting (online, via Zoom), Dissemination strategy circulation, feedback from Partners, Project coordination and management action support, Support for the Project coordination and management, Support for Development of guidelines for target group survey, information delivering to Ayeconomics, Periodical reports implementation, Analysis of needs and competences actions support, English language training program participation, Action dissemination at the international online conference, Support for inner financial management and administration, Inner discussion on TKM partners needs and competences, International Conference participation and project action dissemination (Ashgabat June 12-13, 2020), English language proficiency improving, Periodical reports implementation, Social media and communication review and actions support. | 2020-01-15 | 2020-07-14 | 3 | 47 | 141
Preparation | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.2 | Rustam Gadzhiyev | Manager | WP2 | Inner TKMs Project’s implementation plan, overall preparation to the project implementation, Developing dissemination strategy (drat document), Inner TKM project team meeting, Developing dissemination strategy (permanent communication to all project partners), Support dor Defining Management Board, Dissemination board (DB), Academic Board (AB), Entrepreneurship Centre Manager (ECM), Task Core Groups (TCGs), Dissemination Strategy correspondence, discussion and elaboration, Support for preparation of English language training program and Improving English proficiency of academic staff, Project internal communication with inner and interregional partners, English language training program and Improving English proficiency of academic staff, Participation in the Kick Off Meeting (online, via Zoom), Dissemination strategy circulation, feedback from Partners, Project coordination and management action support, Support for the Project coordination and management, Support for Development of guidelines for target group survey, information delivering to Ayeconomics, Periodical reports implementation, Analysis of needs and competences actions support, English language training program participation, Action dissemination at the international online conference, Support for inner financial management and administration, Inner discussion on TKM partners needs and competences, International Conference participation and project action dissemination (Ashgabat June 12-13, 2020), English language proficiency improving, Periodical reports implementation, Social media and communication review and actions support. | 2020-01-15 | 2020-07-14 | 11 | 47 | 517
Quality Plan | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.2 | Rustam Gadzhiyev | Manager | WP4 | Inner TKMs Project’s implementation plan, overall preparation to the project implementation, Developing dissemination strategy (drat document), Inner TKM project team meeting, Developing dissemination strategy (permanent communication to all project partners), Support dor Defining Management Board, Dissemination board (DB), Academic Board (AB), Entrepreneurship Centre Manager (ECM), Task Core Groups (TCGs), Dissemination Strategy correspondence, discussion and elaboration, Support for preparation of English language training program and Improving English proficiency of academic staff, Project internal communication with inner and interregional partners, English language training program and Improving English proficiency of academic staff, Participation in the Kick Off Meeting (online, via Zoom), Dissemination strategy circulation, feedback from Partners, Project coordination and management action support, Support for the Project coordination and management, Support for Development of guidelines for target group survey, information delivering to Ayeconomics, Periodical reports implementation, Analysis of needs and competences actions support, English language training program participation, Action dissemination at the international online conference, Support for inner financial management and administration, Inner discussion on TKM partners needs and competences, International Conference participation and project action dissemination (Ashgabat June 12-13, 2020), English language proficiency improving, Periodical reports implementation, Social media and communication review and actions support. | 2020-01-15 | 2020-07-14 | 2 | 47 | 94
Development | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.3 | Orazmamed Vasov | Researcher/Teacher/Trainer | WP3 | Inner TKMs Project’s preparation to the project implementation. Support for developing dissemination strategy. Project internal communication with inner and interegional partners. Support for Development of guidelines for target group survey. English language training program participation. International Conference participation and project action dissemination and delivering. English language proficiency improving. Review and improving periodical reports. Project related social media and communication review and actions support. | 2020-01-15 | 2020-07-14 | 3 | 33 | 99
Dissemination & Exploitation | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.3 | Orazmamed Vasov | Researcher/Teacher/Trainer | WP5 | Inner TKMs Project’s preparation to the project implementation. Support for developing dissemination strategy. Project internal communication with inner and interegional partners. Support for Development of guidelines for target group survey. English language training program participation. International Conference participation and project action dissemination and delivering. English language proficiency improving. Review and improving periodical reports. Project related social media and communication review and actions support. | 2020-01-15 | 2020-07-14 | 3 | 33 | 99
Preparation | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.3 | Orazmamed Vasov | Researcher/Teacher/Trainer | WP2 | Inner TKMs Project’s preparation to the project implementation. Support for developing dissemination strategy. Project internal communication with inner and interegional partners. Support for Development of guidelines for target group survey. English language training program participation. International Conference participation and project action dissemination and delivering. English language proficiency improving. Review and improving periodical reports. Project related social media and communication review and actions support. | 2020-01-15 | 2020-07-14 | 3 | 33 | 99
Development | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.4 | Ruben Yegoshin | Technical Staff | WP3 | Inner TKMs Project’s implementation plan, overall preparing to the project implementation, Technical support for developing of dissemination strategy (drat document), Defining Management Board, Dissemination board (DB), Academic Board (AB), Entrepreneurship Centre Manager (ECM), Task Core Groups (TCGs), Project internal communication with inner and interregional partners, Support for developing dissemination strategy, Preparation and analysing for project web site and visual identity and social media, Carrying out Project internal communication with inner and interregional partners, Participation in project internal communication with inner and other partners, Support for creation of project web site and visual identity Participation in Project internal communication with inner and interregional partners, Participating in the inner video conference under the Project, Participation in the English language training program and Improving English proficiency of academic staff | 2020-01-15 | 2020-07-14 | 4 | 22 | 88
Dissemination & Exploitation | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.4 | Ruben Yegoshin | Technical Staff | WP5 | Inner TKMs Project’s implementation plan, overall preparing to the project implementation, Technical support for developing of dissemination strategy (drat document), Defining Management Board, Dissemination board (DB), Academic Board (AB), Entrepreneurship Centre Manager (ECM), Task Core Groups (TCGs), Project internal communication with inner and interregional partners, Support for developing dissemination strategy, Preparation and analysing for project web site and visual identity and social media, Carrying out Project internal communication with inner and interregional partners, Participation in project internal communication with inner and other partners, Support for creation of project web site and visual identity Participation in Project internal communication with inner and interregional partners, Participating in the inner video conference under the Project, Participation in the English language training program and Improving English proficiency of academic staff | 2020-01-15 | 2020-07-14 | 7 | 22 | 154
Management | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.4 | Ruben Yegoshin | Technical Staff | WP1 | Inner TKMs Project’s implementation plan, overall preparing to the project implementation, Technical support for developing of dissemination strategy (drat document), Defining Management Board, Dissemination board (DB), Academic Board (AB), Entrepreneurship Centre Manager (ECM), Task Core Groups (TCGs), Project internal communication with inner and interregional partners, Support for developing dissemination strategy, Preparation and analysing for project web site and visual identity and social media, Carrying out Project internal communication with inner and interregional partners, Participation in project internal communication with inner and other partners, Support for creation of project web site and visual identity Participation in Project internal communication with inner and interregional partners, Participating in the inner video conference under the Project, Participation in the English language training program and Improving English proficiency of academic staff | 2020-01-15 | 2020-07-14 | 6 | 22 | 132
Preparation | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.4 | Ruben Yegoshin | Technical Staff | WP2 | Inner TKMs Project’s implementation plan, overall preparing to the project implementation, Technical support for developing of dissemination strategy (drat document), Defining Management Board, Dissemination board (DB), Academic Board (AB), Entrepreneurship Centre Manager (ECM), Task Core Groups (TCGs), Project internal communication with inner and interregional partners, Support for developing dissemination strategy, Preparation and analysing for project web site and visual identity and social media, Carrying out Project internal communication with inner and interregional partners, Participation in project internal communication with inner and other partners, Support for creation of project web site and visual identity Participation in Project internal communication with inner and interregional partners, Participating in the inner video conference under the Project, Participation in the English language training program and Improving English proficiency of academic staff | 2020-01-15 | 2020-07-14 | 5 | 22 | 110
Preparation | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.5 | Charyyar Amansahedov | Administrative staff | WP2 | Inner TKMs day-to-day action implementation. Full support to UNINA within the project website and visual identity. TKM side project coordination and managment. Analysis of needs and compmetences action support. English language improving. Inner discussion on TKM partners needs and competences. | 2020-07-15 | 2021-01-14 | 13 | 17 | 221
Dissemination & Exploitation | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.5 | Charyyar Amansahedov | Administrative staff | WP5 | Action dissemination, inner meetings. Project newsletter and leaflets dissemination. Preparation of articles and publications. | 2020-07-15 | 2021-01-14 | 10 | 17 | 170
Quality Plan | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.5 | Charyyar Amansahedov | Administrative staff | WP4 | Support to development of guidelines for target group survey | 2020-07-15 | 2021-01-14 | 2 | 17 | 34
Development | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.5 | Charyyar Amansahedov | Administrative staff | WP2 | TUT partner support with Sustainabily Strategy | 2020-07-15 | 2021-01-14 | 2 | 17 | 34
Management | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.5 | Charyyar Amansahedov | Administrative staff | WP1 | Financial management acton support. Equipment of TKM HEIs and subcontracting costs) | 2020-07-15 | 2021-01-14 | 2 | 17 | 34
Preparation | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.6 | Rustam Gadzhiyev | Manager | WP2 | Inner TKM project implementation plan, day to day overall project implementation. Support for development of guidelines for target group survey. | 2020-07-15 | 2021-01-14 | 3 | 47 | 141
Dissemination & Exploitation | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.6 | Rustam Gadzhiyev | Manager | WP5 | Project newsletter and booklet preparation. Dissemination strategy implmentation. Online meeting of the DB and follow-up measures. Full support to UNINA with project website and visula identity. Articles and publications. | 2020-07-15 | 2021-01-14 | 15 | 47 | 705
Management | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.6 | Rustam Gadzhiyev | Manager | WP1 | Inner TKM project meetings. Project coordination and management action support. Participation in online meetings. Financial management action support (equipment for TKM HEIs and subcontracting) | 2020-07-15 | 2021-01-14 | 7 | 47 | 329
Development | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.6 | Rustam Gadzhiyev | Manager | WP2 | English language training program and improving English proficiency of academic staff support. Curriculum presentation to stakeholders discussion. | 2020-07-15 | 2021-01-14 | 7 | 47 | 329
Preparation | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.7 | Orazmamed Vasov | Researcher/Teacher/Trainer | WP2 | Inner TKMs project day to day action support | 2020-07-15 | 2021-01-14 | 1 | 33 | 33
Development | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.7 | Orazmamed Vasov | Researcher/Teacher/Trainer | WP3 | English language training program participation. Action Dissemination support. Support and review and improvement preriodical reports. | 2020-07-15 | 2021-01-14 | 3 | 33 | 99
Dissemination & Exploitation | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.7 | Orazmamed Vasov | Researcher/Teacher/Trainer | WP5 | Project online meeintgs participation. Project related social media communication review and actions support. | 2020-07-15 | 2021-01-14 | 2 | 33 | 66
Preparation | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.8 | Ruben Yegoshin | Technical Staff | WP2 | Inner TKM project implementation plan. Curriculum presentation to stakeholders. Support for TUT in Sustainability and Long-term recommendations methodology. | 2020-07-15 | 2021-01-14 | 5 | 22 | 110
Dissemination & Exploitation | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.8 | Ruben Yegoshin | Technical Staff | WP5 | Technical support for developing Dissemination Strategy. Online meeting of the DB and follow-up measures. Project website and visual identity info allocation. | 2020-07-15 | 2021-01-14 | 7 | 22 | 154
Management | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.8 | Ruben Yegoshin | Technical Staff | WP1 | Carrying out project internal communication with inner and interregional partners. Inner TKM project team meeting. Project coordination and management action support. | 2020-07-15 | 2021-01-14 | 7 | 22 | 154
Development | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | P6.8 | Ruben Yegoshin | Technical Staff | WP3 | Participation in online meeting. Articles publication eleboration action support. | 2020-07-15 | 2021-01-14 | 4 | 22 | 88
[12 empty] | 0 | 0
Management | P7 | Turkmen State Institute of Economics and Management (TSIEM) | Turkmenistan | P7.1 | Shallyyev Charymuhammet | Manager | WP1 | Meeting of the TCM project team. Management and preparation of orientation program. Participation in the Kick-off meeting. Project coordination and management support. | 2020-01-15 | 2020-07-14 | 7 | 47 | 329
Preparation | P7 | Turkmen State Institute of Economics and Management (TSIEM) | Turkmenistan | P7.1 | Shallyyev Charymuhammet | Manager | WP2 | Preparation of required resources to the project implementation. | 2020-01-15 | 2020-07-14 | 2 | 47 | 94
Dissemination & Exploitation | P7 | Turkmen State Institute of Economics and Management (TSIEM) | Turkmenistan | P7.1 | Shallyyev Charymuhammet | Manager | WP5 | Dissemination strategy circulation, feedback from participants. | 2020-01-15 | 2020-07-14 | 1 | 47 | 47
Preparation | P7 | Turkmen State Institute of Economics and Management (TSIEM) | Turkmenistan | P7.2 | Shallyyev Charymuhammet | Manager | WP2 | Day to day overall project implementation. Participation and workshops and surveys. | 2020-07-15 | 2021-01-14 | 2 | 47 | 94
Dissemination & Exploitation | P7 | Turkmen State Institute of Economics and Management (TSIEM) | Turkmenistan | P7.2 | Shallyyev Charymuhammet | Manager | WP5 | Booklet preparation. Preparation of the project handourts and distribution. Online meetings of the DB and follow up measures. Full support to UNINA within the project webstie and visual identity. | 2020-07-15 | 2021-01-14 | 4 | 47 | 188
Management | P7 | Turkmen State Institute of Economics and Management (TSIEM) | Turkmenistan | P7.2 | Shallyyev Charymuhammet | Manager | WP1 | Project coordination and management action support. Student enrolment procedure implementation. Financial management action support. Equipment purchase. | 2020-07-15 | 2021-01-14 | 5 | 47 | 235
Development | P7 | Turkmen State Institute of Economics and Management (TSIEM) | Turkmenistan | P7.2 | Shallyyev Charymuhammet | Manager | WP3 | Participation and support for project professional network. Support for TUT in sustainability and long-term recommendations. | 2020-07-15 | 2021-01-14 | 3 | 47 | 141
0
Preparation | P8 | Turkmen State Institute of Finance (TSIF) | Turkmenistan | P8.1 | Shohrat Byashimov | Manager | WP2 | Preparation of required resources to the project implementation. Preparation of and English course. Dissemination action support. | 2020-01-15 | 2020-07-14 | 3 | 47 | 141
Management | P8 | Turkmen State Institute of Finance (TSIF) | Turkmenistan | P8.1 | Shohrat Byashimov | Manager | WP1 | Meeting of the TCM project team. Management and preparation of orientation program. Participation in the Kick-off meeting. Project coordination and management. | 2020-01-15 | 2020-07-14 | 9 | 47 | 423
Management | P8 | Turkmen State Institute of Finance (TSIF) | Turkmenistan | P8.2 | Kerim Muhammedov | Administrative staff | WP1 | Preparation of required resources to the project implementation. Meeting of the TCM project team. Management and preparation of orientation program. Participation in the Kick-off meeting. Project coordination and management. | 2020-01-15 | 2020-07-14 | 8 | 17 | 136
Dissemination & Exploitation | P8 | Turkmen State Institute of Finance (TSIF) | Turkmenistan | P8.2 | Kerim Muhammedov | Administrative staff | WP5 | Dissemination strategy circulation, feedback from participants. | 2020-01-15 | 2020-07-14 | 2 | 17 | 34
Management | P8 | Turkmen State Institute of Finance (TSIF) | Turkmenistan | P8.3 | Shohrat Byashimov | Manager | WP1 | Meeting of the TSIF project team. Project coordination and management action support. Financial mangement action support. | 2020-07-15 | 2021-01-14 | 8 | 47 | 376
Dissemination & Exploitation | P8 | Turkmen State Institute of Finance (TSIF) | Turkmenistan | P8.3 | Shohrat Byashimov | Manager | WP5 | Project dissemination action support. Full support to UNINA within the project website and visual identity. | 2020-07-15 | 2021-01-14 | 4 | 47 | 188
Preparation | P8 | Turkmen State Institute of Finance (TSIF) | Turkmenistan | P8.3 | Shohrat Byashimov | Manager | WP2 | Participation in workshop and surveys. | 2020-07-15 | 2021-01-14 | 1 | 47 | 47
Development | P8 | Turkmen State Institute of Finance (TSIF) | Turkmenistan | P8.3 | Shohrat Byashimov | Manager | WP3 | Participation and support for porject professional network, social media and communication. | 2020-07-15 | 2021-01-14 | 4 | 47 | 188
Management | P8 | Turkmen State Institute of Finance (TSIF) | Turkmenistan | P8.4 | Kerim Muhammedov | Administrative staff | WP1 | Meeting of the TSIF project team. Project coordination and management action support. | 2020-07-15 | 2021-01-14 | 5 | 17 | 85
Dissemination & Exploitation | P8 | Turkmen State Institute of Finance (TSIF) | Turkmenistan | P8.4 | Kerim Muhammedov | Administrative staff | WP5 | Project dissemination action support. | 2020-07-15 | 2021-01-14 | 3 | 17 | 51
Preparation | P8 | Turkmen State Institute of Finance (TSIF) | Turkmenistan | P8.4 | Kerim Muhammedov | Administrative staff | WP2 | Participation in workshop and surveys. | 2020-07-15 | 2021-01-14 | 1 | 17 | 17
Development | P8 | Turkmen State Institute of Finance (TSIF) | Turkmenistan | P8.4 | Kerim Muhammedov | Administrative staff | WP3 | Support for TUT in Sustainability and long-term recoomendations methodology | 2020-07-15 | 2021-01-14 | 2 | 17 | 34
0
Management | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.1 | Ainura Omarova | Manager | WP1 | Preparation, discussion and approval of organizational documents for the project, Kick-off meeting of MIETC, Coordination of the working group on the passage of English courses, Experts for delphi KEUK, Online meetings | 2020-01-15 | 2020-07-14 | 3 | 77 | 231
Preparation | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.1 | Ainura Omarova | Manager | WP2 | Preparation, discussion and approval of organizational documents for the project, Kick-off meeting of MIETC, Coordination of the working group on the passage of English courses, Experts for delphi KEUK, Online meetings | 2020-01-15 | 2020-07-14 | 1 | 77 | 77
Quality Plan | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.1 | Ainura Omarova | Manager | WP4 | Preparation, discussion and approval of organizational documents for the project, Kick-off meeting of MIETC, Coordination of the working group on the passage of English courses, Experts for delphi KEUK, Online meetings | 2020-01-15 | 2020-07-14 | 2 | 77 | 154
Management | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.2 | Dinara Sergaliyeva | Administrative staff | WP1 | Registration of organizational documents for the project, Preparation of reporting documents, Online meetings. | 2020-01-15 | 2020-07-14 | 6 | 32 | 192
Quality Plan | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.2 | Dinara Sergaliyeva | Administrative staff | WP4 | Registration of organizational documents for the project, Preparation of reporting documents, Online meetings. | 2020-01-15 | 2020-07-14 | 2 | 32 | 64
Preparation | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.3 | Karina Nevmatulina | Manager | WP2 | Preparation, discussion and approval of organizational documents for the project, Kick-off meeting of MIETC, Online meeting, Dissemination of information on the current work of the university in the MIETC project on the official web pages of the university, English training. | 2020-01-15 | 2020-07-14 | 2 | 77 | 154
Management | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.3 | Karina Nevmatulina | Manager | WP1 | Preparation, discussion and approval of organizational documents for the project, Kick-off meeting of MIETC, Online meeting, Dissemination of information on the current work of the university in the MIETC project on the official web pages of the university, English training. | 2020-01-15 | 2020-07-14 | 2 | 77 | 154
Development | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.3 | Karina Nevmatulina | Manager | WP3 | Preparation, discussion and approval of organizational documents for the project, Kick-off meeting of MIETC, Online meeting, Dissemination of information on the current work of the university in the MIETC project on the official web pages of the university, English training. | 2020-01-15 | 2020-07-14 | 2 | 77 | 154
Development | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.4 | Olessya Zhidkoblinova | Researcher/Teacher/Trainer | WP3 | Kick-off meeting of MIETC, English courses, Online meetings, Dissemination of information on the current work of the university in the MIETC project on the official web pages of the university. | 2020-01-15 | 2020-07-14 | 5 | 57 | 285
Preparation | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.5 | Oxana Bezler | Manager | WP2 | Preparation, discussion and approval of organizational documents for the project, Project Coordinator, Development of Concept of Center for Entrepreneurship, Kick-off meeting of MIETC, Coordination of the working group on the passage of English courses, Online meetings, Preparation of reporting documents, English training. | 2020-01-15 | 2020-07-14 | 2 | 77 | 154
Management | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.5 | Oxana Bezler | Manager | WP1 | Preparation, discussion and approval of organizational documents for the project, Project Coordinator, Development of Concept of Center for Entrepreneurship, Kick-off meeting of MIETC, Coordination of the working group on the passage of English courses, Online meetings, Preparation of reporting documents, English training. | 2020-01-15 | 2020-07-14 | 3 | 77 | 231
Quality Plan | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.5 | Oxana Bezler | Manager | WP4 | Preparation, discussion and approval of organizational documents for the project, Project Coordinator, Development of Concept of Center for Entrepreneurship, Kick-off meeting of MIETC, Coordination of the working group on the passage of English courses, Online meetings, Preparation of reporting documents, English training. | 2020-01-15 | 2020-07-14 | 1 | 77 | 77
Management | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.6 | Yelena Stavbunik | Administrative staff | WP1 | Registration of organizational documents for the project, Development of Concept of Center for Entrepreneurship, Preparation of reporting documents, English training. | 2020-01-15 | 2020-07-14 | 4 | 32 | 128
Development | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.6 | Yelena Stavbunik | Administrative staff | WP3 | Registration of organizational documents for the project, Development of Concept of Center for Entrepreneurship, Preparation of reporting documents, English training. | 2020-01-15 | 2020-07-14 | 2 | 32 | 64
Quality Plan | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.6 | Yelena Stavbunik | Administrative staff | WP4 | Registration of organizational documents for the project, Development of Concept of Center for Entrepreneurship, Preparation of reporting documents, English training. | 2020-01-15 | 2020-07-14 | 2 | 32 | 64
Development | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.7 | Yevgenia Puntus | Researcher/Teacher/Trainer | WP3 | Kick-off meeting of MIETC, English courses, Online meetings, Analysis of indicators of the labor market and the market of educational services in the region. | 2020-01-15 | 2020-07-14 | 5 | 57 | 285
Development | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.8 | Ainura Omarova | Manager | WP3 | Development of the curriculum for the Master Program. Content development: discussion of modules structure. | 2020-07-15 | 2021-01-14 | 2 | 77 | 154
Quality Plan | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.8 | Ainura Omarova | Manager | WP4 | Analysis of the implementation of the quality plan, online meetings | 2020-07-15 | 2021-01-14 | 2 | 77 | 154
Management | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.8 | Ainura Omarova | Manager | WP1 | General ccoordination of the working group | 2020-07-15 | 2021-01-14 | 1 | 77 | 77
Development | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.9 | Dinara Sergaliyeva | Administrative staff | WP3 | Discussion of the content of the educational program, Development of the curriculum for the Master Program, Content development: discussion of modules structure | 2020-07-15 | 2021-01-14 | 2 | 32 | 64
Dissemination & Exploitation | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.9 | Dinara Sergaliyeva | Administrative staff | WP5 | Collecting and preparation of information on the implementation of measures for the site, Online meetings | 2020-07-15 | 2021-01-14 | 3 | 32 | 96
Management | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.9 | Dinara Sergaliyeva | Administrative staff | WP1 | Preparation of reporting documents. Project internal communication. | 2020-07-15 | 2021-01-14 | 3 | 32 | 96
Development | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.10 | Karina Nevmatulina | Manager | WP3 | Development of the curriculum for the Master Program, Content development: discussion of modules structure. English training, Dissemination strategy developing, Publication of an article. | 2020-07-15 | 2021-01-14 | 2 | 77 | 154
Quality Plan | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.10 | Karina Nevmatulina | Manager | WP4 | Improvement of the quality plan | 2020-07-15 | 2021-01-14 | 1 | 77 | 77
Management | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.10 | Karina Nevmatulina | Manager | WP5 | Project internal communication and coordination. | 2020-07-15 | 2021-01-14 | 2 | 77 | 154
Development | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.11 | Olessya Zhidkoblinova | Researcher/Teacher/Trainer | WP3 | Development of the curriculum for the Master Program. Developing of the dissemination strategy. Curriculum presentation to steakholders. Content development: structure of modules. English courses. Publication of an article. | 2020-07-15 | 2021-01-14 | 5 | 57 | 285
Development | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.12 | Oxana Bezler | Manager | WP3 | Discussion of the content of the Master Program. Development of the Concept of Entrepreneurship Center. Meetings with employers. Online meetings with partners. | 2020-07-15 | 2021-01-14 | 2 | 77 | 154
Quality Plan | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.12 | Oxana Bezler | Manager | WP4 | Quality plan. English training. | 2020-07-15 | 2021-01-14 | 1 | 77 | 77
Management | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.12 | Oxana Bezler | Manager | WP1 | Financial management and administration. Preparation of the periodical reporting documents. | 2020-07-15 | 2021-01-14 | 2 | 77 | 154
Development | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.13 | Yelena Stavbunik | Administrative staff | WP3 | Development of Concept of the Entrepreneurship Center. Meetings with employers. Study of the experience of the Entrepreneurship Centers. Development of an algorithm for the creation and implementation. of the Entrepreneurship Center. Publication of an article. | 2020-07-15 | 2021-01-14 | 5 | 32 | 160
Quality Plan | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.13 | Yelena Stavbunik | Administrative staff | WP4 | Collection of information for a periodical report | 2020-07-15 | 2021-01-14 | 1 | 32 | 32
Management | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.13 | Yelena Stavbunik | Administrative staff | WP1 | Preparation of reporting documents. Financial administration. | 2020-07-15 | 2021-01-14 | 2 | 32 | 64
Development | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | P9.14 | Yevgenia Puntus | Researcher/Teacher/Trainer | WP3 | Development of questionnaires for potential students and employers. Development of the curriculum for the Master Program. Analysis of the foreign analogue master's programs. Online meetings. English trainings. | 2020-07-15 | 2021-01-14 | 5 | 57 | 285
0
Management | P10 | Technological University of Tajikistan (TUT) | Tajikistan | P10.1 | Sadbarg Boboyorova | Administrative staff | WP1 | Creation of project bank account. Preparation Partnership Agreement for signing. Provision information about TUT project team. Preparation necessary documents for obtaining Schengen Visa, booking the air tickets and accommodation for Kick-off meeting participants. Completion of questionnaire for market need analysis. Preparation and participation on onlne Kick-off meeting. Completion of first period financial reporting. | 2020-01-15 | 2020-07-14 | 12 | 17 | 204
Dissemination & Exploitation | P10 | Technological University of Tajikistan (TUT) | Tajikistan | P10.1 | Sadbarg Boboyorova | Administrative staff | WP5 | Completion of TUT dissemination part of the project dissemination strategy. Completion of final option of project dissemination strategy. | 2020-01-15 | 2020-07-14 | 4 | 17 | 68
Management | P10 | Technological University of Tajikistan (TUT) | Tajikistan | P10.2 | Shokir Mirzoev | Manager | WP1 | Creation of project bank account. Provision information about TUT project team. Preparation of Partnership Agreement draft. Project internal communcation and coordination. Preparation for online Kick-off meeting. Participation in online Kick-off meeting. Preparation of Partnership Agreement draft. Particpation on discussion of budget amendment and correction of TUT project budget. Project internal communcation and coordination. Regular internal communication and coordination. | 2020-01-15 | 2020-07-14 | 13 | 47 | 611
Preparation | P10 | Technological University of Tajikistan (TUT) | Tajikistan | P10.2 | Shokir Mirzoev | Manager | WP2 | Implementation of workshops/ Survey with stakeholders. | 2020-01-15 | 2020-07-14 | 3 | 47 | 141
Development | P10 | Technological University of Tajikistan (TUT) | Tajikistan | P10.3 | Abdurasul Sattorov | Researcher/Teacher/Trainer | WP2 | Provision necessary information for Needs Assessment for English language course. Developing of English language training program and improving English proficiently of academic staff. Completion questionaire for market need analysis. Preparation list of trainees for English language trainings. Developing of English language training program and improving English proficiently of academic staff. Developing of English language training program and improving English proficiently of academic staff. | 2020-01-15 | 2020-07-14 | 13 | 33 | 429
Management | P10 | Technological University of Tajikistan (TUT) | Tajikistan | P10.4 | Sadbarg Boboyorova | Administrative staff | WP1 | Participation on discussion of project budget amendment. Solving the problems regarding to the first transfer. Participation in online meeting. Project internal communication and coordination. Participation in online meeting with representatives of English learning online platform. Project internal communication and coordination. Second period financing reporting. | 2020-07-15 | 2021-01-14 | 7 | 17 | 119
Dissemination & Exploitation | P10 | Technological University of Tajikistan (TUT) | Tajikistan | P10.4 | Sadbarg Boboyorova | Administrative staff | WP5 | Conducting of project info day. Participation in online dissemination meeting. | 2020-07-15 | 2021-01-14 | 2 | 17 | 34
Quality Plan | P10 | Technological University of Tajikistan (TUT) | Tajikistan | P10.4 | Sadbarg Boboyorova | Administrative staff | WP4 | Participation in NEO monitoring | 2020-07-15 | 2021-01-14 | 1 | 17 | 17
Management | P10 | Technological University of Tajikistan (TUT) | Tajikistan | P10.5 | Shokir Mirzoev | Manager | WP1 | Participation on discussion of project budget amendment. Solving the problems regarding to the first transfer. Participation in online meeting. Discussion of the project equipment issues. | 2020-07-15 | 2021-01-14 | 4 | 47 | 188
Preparation | P10 | Technological University of Tajikistan (TUT) | Tajikistan | P10.5 | Shokir Mirzoev | Manager | WP2 | Analysis of needs and competences | 2020-07-15 | 2021-01-14 | 2 | 47 | 94
Quality Plan | P10 | Technological University of Tajikistan (TUT) | Tajikistan | P10.5 | Shokir Mirzoev | Manager | WP4 | Participation in NEO monitoring | 2020-07-15 | 2021-01-14 | 3 | 47 | 141
Development | P10 | Technological University of Tajikistan (TUT) | Tajikistan | P10.6 | Abdurasul Sattorov | Researcher/Teacher/Trainer |  | Preparation proposal for new equipment. Completion of TUT part of project sustainability strategy. Conducting survey for the identification of skill needs. Consideration of details of the English courses. Completion the second round of the survey. Establishment of Entrepreneurs Centers, discussion of equipment issues. Description of the Master Program accreditation process for Tajik Partners. | 2020-07-15 | 2021-01-14 | 12 | 33 | 396
Preparation | P11 | Tajik State University of Commerce (TSUC) | Tajikistan | P11.1 | Zarrina Kadyrova | Manager | WP2 | Prepared project implementation plan. Singned agreements, participated in online meetings. Participation in the Coordinators meeting in Belgium. Meeting with TSUC teachers. | 2020-01-15 | 2020-07-14 | 4 | 47 | 188
Development | P11 | Tajik State University of Commerce (TSUC) | Tajikistan | P11.1 | Zarrina Kadyrova | Manager | WP3 | Developed draft of Sustainability Strategy. Organized selction of teachers of English training and participation in Coursera. Continued development of SS and presentation in online meeting. | 2020-01-15 | 2020-07-14 | 7 | 47 | 329
Dissemination & Exploitation | P11 | Tajik State University of Commerce (TSUC) | Tajikistan | P11.1 | Zarrina Kadyrova | Manager | WP5 | Publish information about the porject in TSUC's website. Contrituted to the development of Dissemination Strategy. | 2020-01-15 | 2020-07-14 | 5 | 47 | 235
Management | P11 | Tajik State University of Commerce (TSUC) | Tajikistan | P11.1 | Zarrina Kadyrova | Manager | WP1 | Communication with partners rearding SS and DS. Participating in online meetings with partners. Assisted professors with Coursera. | 2020-01-15 | 2020-07-14 | 7 | 47 | 329
Preparation | P11 | Tajik State University of Commerce (TSUC) | Tajikistan | P11.2 | Muhammadali Eshov | Administrative staff | WP2 | Assisted in preparation of implementation plan. Conducted english proficiency test, conducting interviews and preparing a list of teaching staff for Coursera. | 2020-01-15 | 2020-07-14 | 11 | 17 | 187
Development | P11 | Tajik State University of Commerce (TSUC) | Tajikistan | P11.2 | Muhammadali Eshov | Administrative staff | WP3 | Assisted in the development of the SS draft. | 2020-01-15 | 2020-07-14 | 8 | 17 | 136
Dissemination & Exploitation | P11 | Tajik State University of Commerce (TSUC) | Tajikistan | P11.2 | Muhammadali Eshov | Administrative staff | WP4 | Translated and published information on the TSUC website about MIETC project. | 2020-01-15 | 2020-07-14 | 3 | 17 | 51
Management | P11 | Tajik State University of Commerce (TSUC) | Tajikistan | P11.3 | Hamidullokhon Fakerov | Manager | WP1 | Consulted during the preparation of implementation plan. Monitored and consulted during the preparation of SS. | 2020-01-15 | 2020-07-14 | 5 | 47 | 235
Development | P11 | Tajik State University of Commerce (TSUC) | Tajikistan | P11.4 | Mubinzhon Abduvaliev | Researcher/Teacher/Trainer | WP3 | Leargin the MIETC'S requirement and it's strateey of sutainability and innovative character. Re-involved the list of trainees and to evaluate their level of English and set an announcement on the university's websites. Providing a roundtable with the university's faculties. Collected data on faculties' performances for OLS modules. Successfullv completed an Advanced Business course within OLS. | 2020-07-15 | 2021-01-14 | 10 | 33 | 330
Development | P11 | Tajik State University of Commerce (TSUC) | Tajikistan | P11.5 | Muhammadali Eshov | Administrative staff | WP1 | Assisted teachers in using coursera platform. Organized online meeting with teachers participating in the project. Updated SS according to partner comments. Preparation of list of teachers for registration in OLS. Learing professional English on OLS platform and assisting teachers through individual consultation. | 2020-07-15 | 2021-01-14 | 15 | 17 | 255
Management | P11 | Tajik State University of Commerce (TSUC) | Tajikistan | P11.6 | Nurmuhammad Abdullozoda | Administrative staff | WP1 | Provide explanation and guidelines regarding Coursera platform to participating teachers. Online meeting with EKSTU about OLS. | 2020-07-15 | 2021-01-14 | 3 | 17 | 51
Development | P11 | Tajik State University of Commerce (TSUC) | Tajikistan | P11.6 | Nurmuhammad Abdullozoda | Administrative staff | WP3 | Open a section on the TSUC website in three languages for dissemination. Posted materials and about project related outcomes on the University website and social media. Liaise with OLS representative and project partners. | 2020-07-15 | 2021-01-14 | 7 | 17 | 119
Management | P11 | Tajik State University of Commerce (TSUC) | Tajikistan | P11.7 | Sadullo Faezov | Administrative staff | WP1 | Management and financial documents - budget and reporting. Consulted the principal of TSUC and project coordinator about rules and regulations related to accounting. Conducted presentation for staff about payments within projects. Prepared documents related | 2020-07-15 | 2021-01-14 | 8 | 17 | 136
Management | P11 | Tajik State University of Commerce (TSUC) | Tajikistan | P11.8 | Zarrina Kadyrova | Manager | WP1 | Management of Coursera with project staff and communication with Kazakh partners. Communication with partners regarding SS. Management of the questionnaires for students and employers. Preparation of the monitoring and presentation of project achievents. | 2020-07-15 | 2021-01-14 | 20 | 47 | 940
0
Preparation | P12 | CTAST | Turkmenistan | P12.1 | Ahmed Akmamedov | Manager | WP2 | Support for the Project coordination and management. Preparednesof to MIETC the articles and publications. English language proficiency improving. | 2020-01-15 | 2020-07-14 | 1 | 47 | 47
Dissemination & Exploitation | P12 | CTAST | Turkmenistan | P12.1 | Ahmed Akmamedov | Manager | WP5 | Support for the Project coordination and management. Preparednesof to MIETC the articles and publications. English language proficiency improving. | 2020-01-15 | 2020-07-14 | 1 | 47 | 47
Development | P12 | CTAST | Turkmenistan | P12.1 | Ahmed Akmamedov | Manager | WP3 | Support for the Project coordination and management. Preparednesof to MIETC the articles and publications. English language proficiency improving. | 2020-01-15 | 2020-07-14 | 1 | 47 | 47
Preparation | P12 | CTAST | Turkmenistan | P12.2 | Ahmed Akmamedov | Manager | WP2 | Online meeting participation. | 2020-07-15 | 2021-01-14 | 1 | 47 | 47
Dissemination & Exploitation | P12 | CTAST | Turkmenistan | P12.2 | Ahmed Akmamedov | Manager | WP5 | Financial management action support (equipment for TKM HEIs and subcontracting costs). | 2020-07-15 | 2021-01-14 | 1 | 47 | 47
Development | P12 | CTAST | Turkmenistan | P12.2 | Ahmed Akmamedov | Manager | WP3 | Support for Development of guidelines for target group survey | 2020-07-15 | 2021-01-14 | 1 | 47 | 47
0
| P13 | FANOVAR | Tajikistan | [8 empty] | 0 | 0
0
| P14 | ECBP | Kazakhstan | [8 empty] | 0 | 0
Total | [10 empty] | 1204 |  | 112198

## Travel&Costs of Stay
WP | P# | PARTNER | COUNTRY | REF. | NAME | STAFF/STUDENT | CITY OF DEPARTURE | CITY OF DESTINATION | DEPARTURE DATE | RETURN DATE | Nº OF DAYS | TRAVEL DISTANCE | MAX. TRAVEL COSTS | MAX. COSTS OF STAY
Preparation | P1 | University of Santiago de Compostela (USC) | Spain | P1.1. | Anne Forryan | staff | Santiago de Compostela | Brussels | 2020-01-26 | 2020-01-28 | 3 | 1319 | 275 | 360
0
0
| P2 | Ayeconomics Research Centre S.L. | Spain | [10 empty] | 0
0
0
| P3 | University of Ljubljana (UL) | Slovenia | [10 empty] | 0
0
0
| P4 | University of Naples Federico II (UNF) | Italy | [10 empty] | 0
0
0
| P5 | East-Kazakhstan State Technical University (EKTSU) | Kazakstan | [10 empty] | 0
0
0
| P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | [10 empty] | 0
0
0
| P7 | Turkmen State Institute of Economics and Management (TSIEM) | Turkmenistan | [10 empty] | 0
0
0
| P8 | Turkmen State Institute of Finance (TSIF) | Turkmenistan | [10 empty] | 0
0
0
| P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakstan | [10 empty] | 0
0
0
| P10 | Technological University of Tajikistan (TUT) | Tajikistan | [10 empty] | 0
0
0
Preparation | P11 | Tajik State University of Commerce (TSUC) | Tajikistan | P11.1. | Zarrina Kadyrova | staff | Moscow | Brussels | 2020-01-26 | 2020-01-29 | 4 | 2252 | 360 | 480
0
0
| P12 | CTAST | [11 empty] | 0
0
0
| P13 | FANOVAR | Tajikistan | [10 empty] | 0
0
0
| P14 | ECBP | Kazakstan | [10 empty] | 0
0
0
Total | [12 empty] | 635 | 840

## Equipment
WORK PACKAGE | PARTNER NUMBER | NAME OF PARTNER | COUNTRY | SUPPORTING DOCUMENT | INVOICE DATE | NATURE, TYPE & SPECIFICATIONS OF THE ITEM | PROVIDING COMPANY | AMOUNT (excluding VAT) | VAT & TAXES (only if charged to project) | TOTAL AMOUNT | CURRENCY | EXCHANGE RATE | AMOUNT CHARGED TO THE PROJECT
Development | P5 | EKTU | Kazakhstan | E-P5.1 | 2020-09-01 | [2] HP W1A29A_S LaserJet Pro MFP M428FDN Printer | LLP Eland | 355035.71 |  | 355035.71 | KZT | 475.55 | 746.5791
Development | P5 | EKTU | Kazakhstan | E-P5.2 | 2020-12-25 | [1] BenQ MW612 Projector | Makarov A.V. | 252000 |  | 252000 | KZT | 475.55 | 529.9127
Development | P5 | EKTU | Kazakhstan | E-P5.3 | 2020-11-20 | [3] PTZ camera CleverMic 3010U | LLP KazNetUniversal | 804000 |  | 804000 | KZT | 475.55 | 1690.674
Development | P5 | EKTU | Kazakhstan | E-P5.4 | 2020-11-12 | [2] CleverMic Hybrid Cable USB 3.0 (50M) | LLP Unit-Technologies | 380000 |  | 380000 | KZT | 475.55 | 799.0748
Development | P7 | TSIEM | Turkmenistan | E-TKM-P7.1 | 2020-11-10 | [4] Desktop Computer (CPU + Cooler + Motherboard + RAM + Case + PSU + HDD + VGA + Keyboard + Mouse + Monitor) | GYRATCOMPUTER | 3890.5 |  | 3890.5 | EUR |  | 3890.5
Development | P7 | TSIEM | Turkmenistan | E-TKM-P7.1 | 2020-11-10 | [2] Web Cam Intex IT-310WC 8.0 mpx | GYRATCOMPUTER | 168 |  | 168 | EUR |  | 168
Development | P7 | TSIEM | Turkmenistan | E-TKM-P7.1 | 2020-11-10 | [4] Printer Canon MF-3010 3.1 LaserJet A4 | GYRATCOMPUTER | 788 |  | 788 | EUR |  | 788
Development | P7 | TSIEM | Turkmenistan | E-TKM-P7.1 | 2020-11-10 | [1] Cartridge JB CB435/36A/CE285A HP LJ P1105/M1120/M1133 | GYRATCOMPUTER | 48 |  | 48 | EUR |  | 48
Development | P8 | TSIF | Turkmenistan | E-TKM-P8.1 | 2020-11-10 | [4] Desktop Computer (CPU + Cooler + Motherboard + RAM + Case + PSU + HDD + VGA + Keyboard + Mouse + Monitor) | GYRATCOMPUTER | 3890.5 |  | 3890.5 | EUR |  | 3890.5
Development | P8 | TSIF | Turkmenistan | E-TKM-P8.1 | 2020-11-10 | [2] Web Cam Intex IT-310WC 8.0 mpx | GYRATCOMPUTER | 168 |  | 168 | EUR |  | 168
Development | P8 | TSIF | Turkmenistan | E-TKM-P8.1 | 2020-11-10 | [4] Printer Canon MF-3010 3.1 LaserJet A4 | GYRATCOMPUTER | 788 |  | 788 | EUR |  | 788
Development | P8 | TSIF | Turkmenistan | E-TKM-P8.1 | 2020-11-10 | [1] Cartridge JB CB435/36A/CE285A HP LJ P1105/M1120/M1133 | GYRATCOMPUTER | 48 |  | 48 | EUR |  | 48
Development | P11 | TSUC | Tajikistan | E-P11.1 | 2021-03-17 | [1] Logitech ConferenceCam Rally Plus Ultra HD (960-001224) | LLC OAZIS | 47882 |  | 47882 | TJS | 12.1351 | 3945.757
Development | P11 | TSUC | Tajikistan | E-P11.1 | 2021-03-17 | [1] MFP M425dn printer/scanner | LLC OAZIS | 7419 |  | 7419 | TJS | 12.1351 | 611.369
Development | P11 | TSUC | Tajikistan | E-P11.1 | 2021-03-17 | [1] BenQ mw612 | LLC OAZIS | 12139 |  | 12139 | TJS | 12.1351 | 1000.3246
Total | [12 empty] | 19112.6912

## Subcontracting
WORK PACKAGE | PARTNER NUMBER | NAME OF PARTNER | COUNTRY | SUPPORTING DOCUMENT | NATURE, TYPE & SPECIFICATIONS OF THE ITEM | PROVIDING COMPANY | VAT & TAXES | AMOUNT | CURRENCY | EXCHANGE RATE | AMOUNT CHARGED TO THE PROJECT
Preparation | P6 | AST | Turkmenistan | P6.1. | Translation of project documentation English-Russian-Turkmen | HJ TOP | 0 | 404.52 | USD | 1.15 | 351.7565
Preparation | P6 | AST | Turkmenistan | P6.2. | Printing of promotional materials | HJ TOP | 0 | 499 | USD | 1.15 | 433.913
Total | [10 empty] | 785.6696

## Data
Distance | Amount | WP |  | Nº | Name of Partner | Country | City (country)
0 KM and 9 KM | 0 | Preparation |  | P1 | University of Santiago de Compostela (USC) | Spain | Santiago de Compostela
10 KM and 99 KM | 20 | Development |  | P2 | Ayeconomics Research Centre S.L. | Spain | Santiago de Compostela
100 KM and 499 KM | 180 | Quality Plan |  | P3 | University of Ljubljana (UL) | Slovenia | Ljubljana
500 KM and 1999 KM | 275 | Dissemination & Exploitation |  | P4 | University of Naples Federico II (UNF) | Italy | Naples
2000 KM and 2999 KM | 360 | Management |  | P5 | East-Kazakhstan State Technical University (EKTSU) | Kazakhstan | Ust-Kamenogorsk
3000 KM and 3999 KM | 530 |  |  | P6 | Academy of Science of Turkmenistan (AST) | Turkmenistan | Ashabad
4000 KM and 7999 KM | 820 | Category |  | P7 | Turkmen State Institute of Economics and Management (TSIEM) | Turkmenistan | Ashabad
8000 KM and more KM | 1500 | Manager |  | P8 | Turkmen State Institute of Finance (TSIF) | Turkmenistan | Ashabad
|  | Researcher/Teacher/Trainer |  | P9 | Karaganda Economic University of Kazpotrebsouz (KEUK) | Kazakhstan | Karaganda
|  | Technical Staff |  | P10 | Technological University of Tajikistan (TUT) | Tajikistan | Dushanbe
Staff | Costs of stay | Administrative staff |  | P11 | Tajik State University of Commerce (TSUC) | Tajikistan | Dushanbe
1-14 days | 120 |  |  | P12 | CTAST | Turkmenistan | Ashabad
15-60 | 70 |  |  | P13 | FANOVAR | Tajikistan | Dushanbe
60-90 | 50 |  |  | P14 | ECBP | Kazakhstan | Ust-Kamenogorsk
Brussels
Student | Costs of stay
1-14 days | 55
15-90 | 40 | Country | Manager | Teacher/Trainer/Researcher | Technical Sataff | Administrative Staff
|  | Spain | 164 | 137 | 102 | 78
|  | Slovenia | 164 | 137 | 102 | 78
|  | Italy | 280 | 214 | 162 | 131
|  | Kazakhstan | 77 | 57 | 40 | 32
|  | Turkmenistan | 47 | 33 | 22 | 17
|  | Tajikistan | 47 | 33 | 22 | 17

## Staff Costs summary
DAYS REPORTED BY CATEGORY | [5 empty] | DAYS REPORTED BY WORKPACKAGE
| Manager | Teacher | Techical | Administrative | TOTAL |  | Management | Preparation | Development | Quality Plan | Dissemination
P1 | 95 | 30 | 10 | 53 | 188 | P1 | 65 | 60 | 18 | 40 | 5
P2 | 15 | 150 | 0 | 0 | 165 | P2 | 5 | 110 | 40 | 10 | 0
P3 | 15 | 15 | 0 | 10 | 40 | P3 | 25 | 9 | 6 | 0 | 0
P4 | 30 | 90 | 8 | 33 | 161 | P4 | 31 | 20 | 75 | 15 | 20
P5 | 40 | 40 | 0 | 33 | 113 | P5 | 81 | 5 | 27 | 0 | 0
P6 | 66 | 15 | 45 | 57 | 183 | P6 | 28 | 50 | 36 | 6 | 63
P7 | 24 | 0 | 0 | 0 | 24 | P7 | 12 | 4 | 3 | 0 | 5
P8 | 29 | 0 | 0 | 21 | 50 | P8 | 30 | 5 | 6 | 0 | 9
P9 | 33 | 20 | 0 | 32 | 85 | P9 | 28 | 5 | 37 | 12 | 3
P10 | 25 | 25 | 0 | 26 | 76 | P10 | 36 | 5 | 25 | 4 | 6
P11 | 48 | 10 | 0 | 55 | 113 | P11 | 43 | 15 | 47 | 0 | 8
P12 | 6 | 0 | 0 | 0 | 6 | P12 | 0 | 2 | 2 | 0 | 2
P13 | 0 | 0 | 0 | 0 | 0 | P13 | 0 | 0 | 0 | 0 | 0
P14 | 0 | 0 | 0 | 0 | 0 | P14 | 0 | 0 | 0 | 0 | 0
| 426 | 395 | 63 | 320 | 1204 |  | 384 | 290 | 322 | 87 | 121
DAYS REPORTED AS RESEARCHER/TEACHER BY WP
[7 empty] | Management | Preparation | Development | Quality Plan | Dissemination
[6 empty] | P1 | 0 | 15 | 15 | 0 | 0
[6 empty] | P2 | 0 | 110 | 40 | 0 | 0
[6 empty] | P3 | 0 | 9 | 6 | 0 | 0
[6 empty] | P4 | 0 | 15 | 75 | 0 | 0
[6 empty] | P5 | 13 | 0 | 27 | 0 | 0
[6 empty] | P6 | 0 | 4 | 6 | 0 | 5
[6 empty] | P7 | 0 | 0 | 0 | 0 | 0
[6 empty] | P8 | 0 | 0 | 0 | 0 | 0
[6 empty] | P9 | 0 | 0 | 20 | 0 | 0
[6 empty] | P10 | 0 | 0 | 25 | 0 | 0
[6 empty] | P11 | 0 | 0 | 10 | 0 | 0
[6 empty] | P12 | 0 | 0 | 0 | 0 | 0
[6 empty] | P13 | 0 | 0 | 0 | 0 | 0
[6 empty] | P14 | 0 | 0 | 0 | 0 | 0
[7 empty] | 13 | 153 | 224 | 0 | 5
DAYS REPORTED AS MANAGER BY WP
[7 empty] | Management | Preparation | Development | Quality Plan | Dissemination
[6 empty] | P1 | 36 | 35 | 3 | 21 | 0
[6 empty] | P2 | 5 | 0 | 0 | 10 | 0
[6 empty] | P3 | 15 | 0 | 0 | 0 | 0
[6 empty] | P4 | 15 | 5 | 0 | 10 | 0
[6 empty] | P5 | 35 | 5 | 0 | 0 | 0
[6 empty] | P6 | 10 | 14 | 14 | 2 | 26
[6 empty] | P7 | 12 | 4 | 3 | 0 | 5
[6 empty] | P8 | 17 | 4 | 4 | 0 | 4
[6 empty] | P9 | 13 | 5 | 8 | 7 | 0
[6 empty] | P10 | 17 | 5 | 0 | 3 | 0
[6 empty] | P11 | 32 | 4 | 7 | 0 | 5
[6 empty] | P12 | 0 | 2 | 2 | 0 | 2
[6 empty] | P13 | 0 | 0 | 0 | 0 | 0
[6 empty] | P14 | 0 | 0 | 0 | 0 | 0
[7 empty] | 207 | 83 | 41 | 53 | 42
DAYS REPORTED AS TECHNICIAN BY WP
[7 empty] | Management | Preparation | Development | Quality Plan | Dissemination
[6 empty] | P1 | 0 | 10 | 0 | 0 | 0
[6 empty] | P2 | 0 | 0 | 0 | 0 | 0
[6 empty] | P3 | 0 | 0 | 0 | 0 | 0
[6 empty] | P4 | 0 | 0 | 0 | 0 | 8
[6 empty] | P5 | 0 | 0 | 0 | 0 | 0
[6 empty] | P6 | 13 | 10 | 8 | 0 | 14
[6 empty] | P7 | 0 | 0 | 0 | 0 | 0
[6 empty] | P8 | 0 | 0 | 0 | 0 | 0
[6 empty] | P9 | 0 | 0 | 0 | 0 | 0
[6 empty] | P10 | 0 | 0 | 0 | 0 | 0
[6 empty] | P11 | 0 | 0 | 0 | 0 | 0
[6 empty] | P12 | 0 | 0 | 0 | 0 | 0
[6 empty] | P13 | 0 | 0 | 0 | 0 | 0
[6 empty] | P14 | 0 | 0 | 0 | 0 | 0
[7 empty] | 13 | 20 | 8 | 0 | 22
DAYS REPORTED AS ADMINISTRATIVE BY WP
[7 empty] | Management | Preparation | Development | Quality Plan | Dissemination
[6 empty] | P1 | 29 | 0 | 0 | 19 | 5
[6 empty] | P2 | 0 | 0 | 0 | 0 | 0
[6 empty] | P3 | 10 | 0 | 0 | 0 | 0
[6 empty] | P4 | 16 | 0 | 0 | 5 | 12
[6 empty] | P5 | 33 | 0 | 0 | 0 | 0
[6 empty] | P6 | 5 | 22 | 8 | 4 | 18
[6 empty] | P7 | 0 | 0 | 0 | 0 | 0
[6 empty] | P8 | 13 | 1 | 2 | 0 | 5
[6 empty] | P9 | 15 | 0 | 9 | 5 | 3
[6 empty] | P10 | 19 | 0 | 0 | 1 | 6
[6 empty] | P11 | 11 | 11 | 30 | 0 | 3
[6 empty] | P12 | 0 | 0 | 0 | 0 | 0
[6 empty] | P13 | 0 | 0 | 0 | 0 | 0
[6 empty] | P14 | 0 | 0 | 0 | 0 | 0
[7 empty] | 151 | 34 | 49 | 34 | 52